EMIS — Project Management and Risk Plan

Project: Design and Development of a Privacy-Aware QR/NFC-Based Emergency Medical Information System

Purpose: Document team responsibilities, milestone planning, task traceability, dependencies and risks. This document records reported progress; it is not evidence that planned backend or QR/NFC features are implemented.

1. Team and Responsibilities

| Contributor | Primary responsibility | Evidence / expected outputs |
| --- | --- | --- |
| Bekbolat Yergaliuly | Frontend and coordination | Next.js frontend setup, emergency profile interface, repository coordination |
| Shugyla Akhit Zhasulankyzy | UI/UX and design documentation | Mobile/desktop Figma mockups, card concept, scanning journey, design report |
| Olzhas Omerzak Zhunisbekuly | Backend architecture and planned implementation | Backend README / architecture plan; future Spring Boot API and persistence |
| Supervisor: Dana Yespenbetova | Academic review | Feedback on scope, architecture, research and milestones (to be collected) |

2. Scope and Delivery Strategy

Current pre-defense emphasis: problem definition, prototype, architecture, technology rationale, requirements, planning and traceable contributions. A complete working application is not required at this stage.

In scope (planned system): public emergency summary accessed by QR/NFC; owner-managed private medical data; emergency contact; authentication and access controls; auditability and privacy safeguards.

Out of scope for the first pre-defense: operational Spring Boot API, production database, deployed QR/NFC cards, clinical validation, and real-patient medical data. All examples should use fictional data.

3. Current YouTrack Progress (reported 23 October 2026)

| Issue | Work item | Status |
| --- | --- | --- |
| EMIS-1 | Initialize Next.js frontend | Done |
| EMIS-2 | Design emergency profile in Figma | Done |
| EMIS-3 | Initialize Spring Boot backend | In development / not complete |
| EMIS-5 | Develop emergency medical profile UI | Done |
| EMIS-6 | Create UI/UX design documentation | Done |
| EMIS-7 | Develop emergency medical profile API | Backlog / not complete |
| EMIS-8 | Prepare backend architecture documentation | Done (per team report) |

The task snapshot above reflects the team’s reported board state and should be cross-checked against the latest YouTrack export before submission. Other documentation tasks added later should be included in the final snapshot.

4. Milestones and Dependencies

| Milestone | Target / stage | Dependencies |
| --- | --- | --- |
| First pre-defense package | 24 October 2026 | Reviewed docs, GitHub PR evidence, YouTrack board, prototype, supervisor review |
| Backend foundation | After first pre-defense | Architecture confirmation, environment setup, collaborator access |
| Profile API and database | Next implementation stage | Backend foundation, approved data model, privacy rules |
| QR/NFC end-to-end integration | After API readiness | Stable URL resolution, public profile endpoint, frontend integration |
| Security, usability and evaluation | Before final defense | Integrated system, test data, defined baseline and metrics |

5. Risk Register

| Risk | Likelihood / impact | Mitigation and owner |
| --- | --- | --- |
| Sensitive medical information exposed | Medium / High | Public/private field separation; access tests; no real patient data. Backend + frontend |
| Backend delayed | High / Medium | Submit architecture plan now; sequence API work after setup. Olzhas |
| QR/NFC card fails or becomes inaccessible | Medium / Medium | QR fallback, short stable URL, test multiple devices. Team |
| Inconsistent mockup data or terminology | Medium / Medium | Unify example patient, blood group and contacts. Shugyla + Bekbolat |
| Unverified clinical content | Medium / High | Avoid diagnosis/treatment claims; review emergency text with qualified sources. Team |
| Incomplete research or supervisor evidence | High / High | Track missing deliverables explicitly; request real feedback; no fabricated interviews. Team |
| Untraceable GitHub contributions | Medium / High | Individual accounts, task IDs, reviewed PRs and links to YouTrack. Team |